GOVERNMENT OF INDIA

MINISTRY OF RAILWAYS

RAJYA SABHA

UNSTARRED QUESTION  NO. 3246

TO BE ANSWERED ON 04.05.2012

PROPOSALS FROM GOVERNMENT OF MADHYA PRADESH

3246.  SHRI RAGHUNANDAN SHARMA:

Will the Minister of RAILWAYS be pleased to state:

(a) the number of proposals regarding Railways received by Central Government from Government of Madhya Pradesh, during the period 2004 to 2011;

(b)  out of them how many proposals have been cleared and how many are lying pending and by when these proposals would be cleared; and

(c)  the details thereof?

ANSWER

MINISTER OF STATE IN THE MINISTRY OF RAILWAYS

(SHRI BHARATSINH SOLANKI)

(a) to (c): A Statement is laid on the Table of the House.

*****

STATEMENT REFERRED TO IN REPLY TO PART (a) TO (c) OF UNSTARRED QUESTION NO.3246 BY SHRI RAGHUNANDAN SHARMA TO BE ANSWERED IN RAJYA SABHA ON 04.05.2012 REGARDING PROPOSALS FROM GOVERNMENT OF MADHYA PRADESH

(a) to (c):  Details of Railway proposals received  from Government  of Madhya Pradesh  from 2004 onwards  is not available in record.  However, on 15.11.2011 Chief Minister, Madhya Pradesh had sent a list of important Railway projects in Madhya Pradesh. The status of these projects is as under:-

| S.No. | Name of the Project | Present Status |
| --- | --- | --- |
| 1. | Gauge Conversion of Jabalpur-Gondia rail line | On this project, Gondia-Balaghat (422 km) and Balaghat-Katangi (47 km) have been completed and commissioned. Contracts for earthwork and bridges in Balaghat-Nainpur-Jabalpur awarded but work is held up for want of forestry clearance. |
| 2. | New rail line from Makroniya RS of Sagar to Khajuraho via Karrapur-Dabanga-Dalpatpur-Shahgarh-Heerapur-Bada Malhera | A survey for construction of a new Broad Gauge (BG) line from Chhindwara-Gadarwara-Udaipur-Jaisinagar-Saugor-Banda Badamalhara-Khajuraho Rail line is included in the Budget 2012-13. |
| 3. | New rail line between Bhind and Konch via Lahar | A survey for construction of a new BG line between Bhind and Konch via Lahar is included in the Budget 2012-13. |
| 4. | Conversion of narrow gauge line between Gwalior and Sheopur into BG and extending it upto Kota | Gwalior-Sheopur Kalan Gauge Conversion (GC) with extension upto Kota (284 km) is a sanctioned work. Final Location Survey (FLS) has been taken up. |
| 5. | Construction/extension of new line from Indore to Manmad via Khargaon-Sendhwa | Manmad-Indore via Malegaon & Dhule new line is not a sanctioned work. However, the proposal has been sent to Planning Commission for according “In Principle” approval. |
| 6. | Construction of Indore-Dahod, Indore-Chota Udaipur railway line | Dahod-Indore part estimate for Dahod-Katwara and Sagar-Indore has been sanctioned. Earthwork and bridge contract awarded where land is available. Target for completion not yet fixed. On Chhotaudepur-Dhar section, earthwork and bridges taken up in first 40 km stretch where more than 50% land has been acquired. Target date for completion not yet fixed. |
| 7. | Construction of new rail line from Indore to Manmad via Barwani | Survey completed. Updated cost and Rate of Return (ROR) of the project after cost sharing received recently. Under process. |
| 8. | Conversion of Ratlam-Indore-Khandwa-Akola MG rail line into BG | Part detailed estimate for Ratlam-Indore-Mhow (159.45 km) and Akola-Akod (43.5 km) sections sanctioned. Ratlam-Fatehabad (80 km) is targeted for completion by March 2013. |
| 9. | Construction of new rail line between Lalitpur-Singrauli | On this project, Mahoba-Khajuraho (65 km) already completed and commissioned. On Lalitpur-Mawaikhas-Kharagpur (87 km) completed in 2011-12. Work taken up in Sidhi-Singrauli section. In Khajuraho-Satna section, Ministry of Environment & Forests (MOEF) has not cleared the alignment passing through Panna Wild Life Reserve and alternate alignment is being explored. |
| 10. | Starting work on the Indore-Dhar-Udaipur route, expediting the new line work from Indore to Dahod and linking Indore to Khandwa on BG which falls under Delhi-Mumbai Industrial | Gwalior-Sheopur Kalan GC project with extension upto Kota (284 km) has been sanctioned. FLS taken up. |
| 11. | Providing linkage to Panna with Satna new rail line | Panna-Satna section is a part of sanctioned Lalitpur-Satna-Rewa-Singrauli new line project. In Khajuraho-Satna section, FLS taken up avoiding Panna Wildlife Sanctuary. |

*****