
STATEMENT REFERRED TO IN REPLY TO PARTS (a) & (b) OF STARRED QUESTION NO. 179 BY SHRI BIRENDRA PRASAD BAISHYA TO BE ANSWERED IN RAJYA SABHA ON 08.03.2013 REGARDING STATUS OF RAILWAY PROJECTS UNDER NFR

(a): A dedicated Non-Lapsable North Eastern Region Rail Development Fund has been created for ensuring assured cash flow for execution of National Projects of N.E. Region.  Minimum 10% of funds to  projects of North East Region are provided for ensuring adequate cash flow for projects of N.E. Region. 
The details of railway projects including National Projects in NE Region are as under:-
                                								(Rs.in crore)
	S.No.
	Name of the Project
	Latest anticipated  cost
	Outlay 2012-13
	Expenditure upto March, 2013
	Proposed outlay 2013-14
	Status

	NEW LINE

	1.
	Agartala-Sabroom
	1141.75
	180.00
	327.8
	140.00
	This is a ‘National Project’. Land acquisition, earthwork and bridge works taken up. 
Target –December, 2015

	2.
	Teteliya-Byrnihat
	385.2
	70.00
	93.11
	50.00
	This is a ‘National Project’. Teteliya-Byrnihat was examined as an alternative alignment to Azara-Byrnihat. Entire land acquired in Assam portion. Earthwork and bridges taken up. Target – March. 2015.

	3.
	Bhairabi-Sairang
	2393.48
	80.00
	4.41
	77.10
	This project has been declared as ‘National Project’. Estimate sanctioned and tender for earthwork and bridges called. Target – March, 2015.

	4.
	Bogibeel Bridge with link lines on North and South Banks
	3230.02
	330.00
	2380.64
	340.00
	The project has been declared as ‘National Project’. The work of construction of embankment, major and minor bridges completed in North and South Bank of the bridge. Moranhat-Chalkhowa (44 km) in South Bank completed and commissioned. Contract for main bridge superstructure awarded. Target – December, 2015.

	5.
	Dimapur-Kohima (Zubza)
	850.00
	7.00
	8.97
	1.00
	The project has been declared as ‘National Project’. Final Location Survey completed in the entire length. Project held up for want of approval of alignment by State Government and exorbitant land rates. TDC: Not fixed.

	6.
	Dudhnoi-Mendipathar
	178.47
	20.00
	45.64
	40.00
	Earthwork, bridges and track work in advance stages of execution. 10 km targeted for completion in 2012-13 and rest in 2013-14. 

	7.
	Harmuti-Naharlagun
	415.73
	50.00
	232.34
	60.00
	Track linking for 20 kms completed in 2011-12. Commissioning is linked with completion of Rangpara North – North Lakhimpur gauge conversion. Project targeted for completion in 2013-14.

	8.
	Jiribam-Tupul-Imphal
	4444
	450.00
	681.94
	453.90
	Progress of this ‘National Project’ badly hampered due to prevailing security scenario and frequent bandhs etc. Bad condition of NH 53 and weak/damaged bridges.  Earthwork, formation, minor and major bridges taken up. Work taken up in 18 tunnels out of 35 Nos. Jiribam-Tupul targeted for completion by March, 2015 and Tupul-Imphal by March, 2017.

	9.
	New Maynaguri-Jogighopa
	1655.81
	225.00
	1056.22
	140.00
	Work is planned to be executed in 4 phases. Golakganj to Gauripur completed. New Coochbehar-Golakganj (58.0 km) completed. Gauripur- New Changrabandha-New Coochbehar  targeted for  2012-13.

	10.
	Sivok-Rangpo
	3380.58
	38.00
	52.63
	25.00
	This is a ‘National Project’ which has been entrusted to M/s IRCON for execution.  Project held up for environmental clearance.

	11.
	Byrnihat-Shillong
	4083.02
	30.00
	1.5
	1.00
	Final Location Survey from Byrnihat to Lailad (20 km) completed. Work stopped in November, 2010 by Khasi Students Union for their pending demands. Matter taken up with  State Government.

	12.
	Murkongselek-Pasighat
	165.82
	10.00
	0.15
	1.00
	Final Location Survey taken up.
Target : March, 2015 

	13.
	Agartala-Akhaura
	252.00
	1.00
	0
	10.00
	

	             GAUGE CONVERSION

	1.
	Katakhal-Bhairabi
	223.01
	15.00
	103.48
	15.00
	The work planned for completion alongwith gauge conversion of Lumding-Silchar in March, 2014.
Overall progress: 51.42%

	2.
	Lumding-Silchar including alignment between Migrendisa-Ditokcherra and extension from Badarpur to Baraigram
	4255.37
	400.00
	3013.49
	-
	The project has been declared as ‘National Project’. Progress of work affected due to militant activities. Earthwork, bridge works and tunneling taken up all along the alignment. Target – March, 2015.
Overall physical progress: 75.90%

	3.
	New Jalpaiguri-Siliguri-New Bongaigaon branch lines
	1308.9
	10.00
	1023.41
	-
	New Jalpaiguri-New Bongaigaon main line fully commissioned. Alipurduar-Bamanhat and Fakiragram-Dhubri branch line completed and commissioned.

	4.
	Rangiya-Murkong-
selek alongwith linked fingers
	1717.29
	380.00
	1107.75
	425.00
	Mega block taken up for entire section. Rangiya-Rangpara North section completed and engine rolled. Rangpara North-North Lakhimpur (172 km) targeted for March, 2013North Lakhimpur-Murkongselek section targeted in 2013-14. 

	DOUBLING

	1.
	Lumding-Hojai Patch Doubling
	246.07
	1.00
	0
	2.00
	Work included in Budget 2012-13. 



(b): (i) The details of wagon factories are as under:-
(Rs. in crores)
	S.No.
	Name of the project
	Latest anticipated cost
	Outlay 2012-13
	Expenditure upto March,2013
	Proposed outlay 2013-14
	Status

	1.
	Wagon Manufacturing factory at Guwahati
	188.50 (PPP)
	20.00 (PPP)
	Nil
	2.00
	The project has been sanctioned under Public Private Partnership mode.  M/s IRCON has been appointed as consultant for bid process management.  The process is under progress.

	2.
	EMD loco shed for homing 50 locos at Mariani
	48.11
	2.00
	Nil
	1.94
	Detailed plans and estimates of the project have been sanctioned.  The work is in progress.






(ii) 	The details about Kendriya Vidyalaya are as under:
In the Rail Budget 2010-11, it was announced that 50 Kendriya Vidyalays will be set up on the Railways for benefit of Railway wards.  A Memorandum of Understanding was signed with Ministry of Human Resource Development (HRD) for setting up said 50 Kendriya Vidyalays on the Railways.  Pursuant thereto 50 locations on the Railways were suggested to Kendriya Vidyalaya Sangathan which included 05 locations on NF Railway namely at Rangiya, Rangapara, North Lakhimpur, New Jalpaiguri and New Coochbeehar.  Kendriya Vidyalaya Sangathan has since sanctioned one Kendriya Vidyalaya at Railway Campus, Rangiya (Assam) and the school has started functioning on temporary basis.  Ministry of HRD has been requested to consider opening of Kendriya Vidyalayas at remaining 43 locations including 04 on NF Railway.

(iii)	The details of Multi-Speciality Hospital are as under:-
A Memorandum of Understanding (MoU) was between Ministry of Railways and Ministry of Health and Family Welfare to set up health care infrastructure on vacant Railway land which is not immediately operationally required. Consequent to signing of MoU, in the Budget 2010-11 it was announced to set up 522 health care infrastructures consisting of OPD & Diagnostic Centre, Secondary Level General Specialty Hospitals and Tertiary Care Hospitals. Ministry of Health & Family Welfare is the nodal Ministry for setting up of these healthcare projects Guwahati, Katihar, New Bongaigaon, New Jalpaiguri, New Mal, Rangapara North and Siliguri Jn have been identified for setting up of Tertiary Level Multi Specialty Hospitals. To operationalize the MoU, 91 locations have been identified for a pilot project by the High Power Working Group consisting of the senior officials from both the Ministries. New Bongaigaon and Ranagapara North are included in this pilot project. Further, Ministry of Health & Family Welfare has appointed M/s IL & FS as Transaction Advisor for this project.
(iv)	New trains between Kamakhya-Tezpur:	
In Rangiya-Rangapara North – Tezpur section, track linking works had been completed in March, 2012. Commissioner of Railway Safety is expected to inspect the section in March, 2013 end. After getting clearance from Commissioner of Railway Safety, the passenger/mail Express trains  can  be introduced in the section.
*****



