APPENDIX REFERRED TO IN REPLY TO PART (b) OF UNSTARRED QUESTION NO. 1853 BY SHRI BIRENDRA PRASAD BAISHYA TO BE ANSWERED IN RAJYA SABHA ON 07.02.2014 REGARDING PROJECTS IN NER.
(b):  Project-wise details of National Projects in North East Region (NER) is given below:-  

	S. No.
	Name of project
	Cost
2013-14
	Expenditure upto
March, 2013
	Outlay
2013-14
	Reasons for delay

	
	
	(` in Crore)
	

	           New Line



	1
	Agartala-Sabroom new line (110 km)
	1141.75
	497.8
	140
	Land acquisition not complete. 

	2
	Bhairabi-Sairang (51.38 km)
	2393.48
	101.81
	77.1
	Acquisition of forest land required for this project is not complete.

	3
	Bogibeel bridge with linking lines between Dibrugarh and North Bank line (46 km)
	4500
	2760.64
	340
	Land acquisition not complete. 

	4
	Byrnihat-Shillong (108.40 km)

	4083.02
	2.5
	1
	Land acquisition not complete. 

	5
	Dimapur-Kohima (88 km)
	850
	9.44
	1
	Land acquisition not complete. 

	6
	Jiribam-Imphal (97.90 km)
	4478.17
	1229.94
	453.9
	Public outrage and non conducive security scenario. 

	7
	Sivok-Rangpo (44.39 km)
	3380.58
	102.63
	25
	Awaiting forest land clearance.

	8
	Teteliya-Byrnihat (21.50 km)
	385.2
	153.11
	50
	Land acquisition not complete. 

	          Gauge Conversion

	9
	Lumding-Silchar including Migrendisa-Dittockchera (198 km), extension Badarpur-Bairagram (44 km) & new Material Modification  for Gauge Conversion of Baraigram-Dulabchera with bypass at Karimganj (29.40 km) & Karimganj-Maishashan (10.30 km)
	4255.37
	3413.49
	375
	Extortion and militant threat have contributed. Forestry clearance received only in 2013.

	10
	Rangiya-Murkongselek alongwith linked fingers (510.33 km)
	2232.5
	1487.75
	425
	88% work completed. Delayed due to fund constraint.
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