GOVERNMENT OF INDIA

MINISTRY OF SHIPPING

RAJYA SABHA

UNSTARRED QUESTION NO.832

TO BE ANSWERED ON  25th  JULY, 2016

DEVELOPMENT OF SEA PORT IN SAGAR ISLAND

832.   SHRI MD. NADIMUL HAQUE:

Will the Minister of SHIPPING be pleased to state:

(a) 	   whether it is a fact that the development of sea port at Sagar island has been delayed; ;

(b)	if so, the details thereof; (c) the details of timeline for development of port there; (d) the details of   funds allocated for 186 development of the port along with the detailed break-up; and

(e) 	the feasibility of developing a sea port at sagar islands?

ANSWER

MINISTER OF STATE IN THE MINISTRY OF SHIPPING

(SHRI  PON RADHAKRISHNAN)

(a)&(b): No, Sir.

(c):	       The timeline for development of Sagar Port is at Annexure-A.

(d):	       The cost of the project as per Revenue Model is estimated at INR 1464 crores. The work related to reclamation, dredging and provision of basic infrastructure will be undertaken by Special Purpose Vehicle (SPV) and Kolkata Port Trust.  Total cost of these works is estimated to be Rs.515 crores. The construction of port related infrastructure like berths etc. will be undertaken by the concessionaire at an estimated cost of Rs. 948.6 crores. The break-up of cost is at Annexure - B.

The Project is now being taken for Phase-I. The total Phase-I cost of Sagar Port Development has been estimated to Rs. 1464 crores.

(e):	        Kolkata Port has been facing the challenges in terms of draft limitations, limited headroom for expansion and efficiency. The constraints has necessitated the need to have an alternative port near to sea, having sufficient draft and no river navigation, as it has been there in Kolkata Port.

Sagar Island has been selected after a detailed study for locating the port. A new port in Sagar will share the hinterland of the Haldia and Kolkata ports, particularly the power and steel plants in the eastern region, and containers from the eastern parts of India (Western UP, Odisha, Jharkhand, Chhattisgarh etc.) and neighboring landlocked countries- Nepal and Bhutan. The port will be a viable alternative to serve as for spill-over cargo, specifically non-POL bulk from the Haldia dock complex.

Containers will be another major variant to be handled at the Sagar port.  This is primarily due the limitation of capacity and the inability to expand the Haldia and Kolkata ports, which can result in an overflow of containers that can be handled at the Sagar port.

The traffic for the Sagar port is projected to be around 3.5 MTPA in 2020 increasing to around 27 MTPA in 2035.

…2/-

- 2        -

ANNEXURE-A

Details of timeline of development of Sagar Port

| ACTIVITY | TIMELINE |
| --- | --- |
| PPPAC Presentation | 22 March 2016 |
| Preparation of bid documents (including reclamation and dredging) | Already submitted to PPPAC and MOS |
| PPPAC Approval to be recd*+ | Awaited |
| EFC Memo** | 07 June 2016 |
| Notification of Port Limits | 24 June 2016 |
| CCEA Approval To Be Recd* | Awaited |
| TOR Amendment Presentation | 29 July 2016 |
| RFQ Issue Date | 20 August 2016 |
| Last date of receiving RFQ queries | 16 September 2016 |
| Pre-application conference (RFQ) | 22 September 2016 |
| Authority response to queries | 29 September 2016 |
| Application due date (RFQ) | 09 October 2016 |
| Announcement of short list of applicants | 26 October 2016 |
| RFP Issuance Date | 03 November 2016 |
| CRZ Recommendation from State Coastal Zone Management Authority (SCZMA) | 07 November 2016 |
| Final application to MoEF & CC for Environmental Clearance (EC) with final EIA report to be submitted | 30 November 2016 |
| RFP Submission Date | 18 December 2016 |
| Security clearance to be obtained | 31 December 2016 |
| Letter of Award | 31 January 2017 |
| Environmental Clearance | 28 February 2017 |
| Signing of Concession Agreement | 28 February 2017 |

*Indicated by MoS

+The Sagar Port proposal decision was postponed at the PPPAC meeting held on March 22, 2016.

**EFC Memo for approval of INR 515 Cr as grant to execute the works by BSPL was submitted in June, 2016. After EFC approval of the grant for INR 515 Cr, the RFQ, RFP and DCA already prepared for selection of Concessionaire will be updated as per the suggested amendments which will be further be submitted to PPPAC and CCEA for approval. Preparation of draft Tender documents for basic infrastructure, land reclamation and dredging related activities undertaken by SPV will be initiated after approval of EFC Memo

Please note that the dates mentioned above are subject to change after EFC Approval.

…3/-

-     3      -                                                ANNEXURE-B

(Rs. in crores)

| S.No. | Works | SPV EPC Model | PPP (DBFOT Model) |
| --- | --- | --- | --- |
| 1. | Dredging | 28.2 |  |
| 2. | Land Reclamation, Clearing & Land Improvement | 324.3 | 8.3 |
| 3. | Common Infrastructure Facilities (Administration building, Gate House, Customs Building, Harbour Master Block and control room, Signal Station, Fire Station building, Users building, etc.) |  | 92.4 |
| 4. | Development of Berths & Cargo Terminal (Berthing Jetty, Approach Trestle, Stack Yard, Paved storage yard, Other Miscellaneous works) |  | 346.8 |
| 5. | Cargo Handling Equipment |  | 276.5 |
| 6. | Navigational aids | 2 |  |
| 7. | Harbour Crafts & locomotives |  |  |
| 8. | Provision of External Power | 11.5 | 45.7 |
| 9. | Provision of Water supply. |  | 2.4 |
| 10. | Provision of Telecommunication |  | 5.9 |
| 11. | External Road | 32.8 |  |
| 12. | Internal Main / Secondary Roads to Operational Areas and Parking |  | 18.9 |
| 13. | Railway Lines and Rail Yard in Mainland | 67.1 |  |
| 14. | Contingencies @ 15% | 23.1 | 41.3 |
| 15. | Environment Aspects |  | 12 |
| 16. | Fire Fighting System/ Hazard Mitigation |  | 12 |
| 17. | Project management & Engineering consultancy |  | 5.3 |
|  | TOTAL | 489 | 867.5 |
| 18. | Other costs (EIA, VTMS, IDC, etc.) | 26.4 | 81.1 |
|  | TOTAL COST OF THE PROJECT | 515.4 | 948.6 |

*****