GOVERNMENT OF INDIA
MINISTRY OF DEFENCE
DEPARTMENT OF DEFENCE PRODUCTION  
RAJYA SABHA
 UNSTARRED QUESTION NO.2086
TO BE ANSWERED ON 6.8.2018

          
PRODUCTION OF TEJAS AIRCRAFT

2086.  	SHRI HARIVANSH:
	          
Will the Minister of DEFENCE be pleased to state:

(a) the total time required and cost incurred to manufacture Tejas fighter planes;


(b) the total number of Tejas fighter planes handed over to the Indian Air Force, so far;

(c) the future plans with respect to these fighter planes; and

(d) the details thereof?


             ANSWER
MINISTER OF STATE IN THE MINISTRY OF DEFENCE
DR. SUBHASH BHAMRE



(a) & (b):  For production of  Light Combat Aircraft (LCA) Tejas, Hindustan Aeronautics Limited (HAL) has got orders from Indian Air Force (IAF) for 40 aircrafts {20 Initial Operational Clearance (IOC) standard and 20 Final Operational Clearance (FOC) standard}.  20 IOC contract was signed on 31st March 2006 to be completed by December 2011 and 20 FOC contract was signed on 23rd December 2010 to be completed by 2016.  IOC for LCA Tejas was received in December, 2013.
The value of IOC contract for 20 No. Tejas aircrafts is Rs.2701.70 Crores (Revised to Rs.2812.91 Crores).  Amendment in IOC contract has been sought for Rs.5362.17 Crores as part of Change Order on account of changes in build standards for Integration entailing procurement of additional Line Replaceable Units (LRUs), Raw materials, composite materials, Bought out items and consumables, tooling etc.
The value of FOC contract for 20 Tejas aircrafts is Rs.5989.39 Crores.
Out of total 20 IOC aircrafts, 9 aircrafts have been delivered by HAL to IAF till date.
(c) & (d):  Besides, 40 LCA Tejas aircrafts (20 IOC & 20 FOC), Defence Acquisition Council (DAC) has cleared acquisition of 83 LCA Mk1A aircraft with enhanced capabilities with Active Electronically Scanned Array (AESA) Radar, Beyond Visual Range (BVR) Missile, Self-Protection Jammer (SPJ) and Air-to-Air Refuelling (AAR) for which quotation has been submitted by HAL.
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