GOVERNMENT OF INDIA

MINISTRY OF ROAD TRANSPORT AND HIGHWAYS

RAJYA SABHA

UNSTARRED QUESTION NO-433

ANSWERED ON-03/12/2025

RANCHI-VARANASI ECONOMIC CORRIDOR

433.     SMT. MAHUA MAJI:

Will the Minister of ROAD TRANSPORT AND HIGHWAYS be pleased to state:

(a)	whether it is a fact that out of the Central Government's 413-kilometre-long Ranchi-Varanasi Economic Corridor, only 60 percent construction of the 253-kilometre section of Jharkhand has been completed so far, if so, the details thereof; and

(b)	Whether it is a fact that in some areas there are delays in obtaining approval from the Forest Department, which has stalled the construction work, if so, the details thereof?

ANSWER

THE MINISTER OF ROAD TRANSPORT AND HIGHWAYS

(SHRI NITIN JAIRAM GADKARI)

(a)	The current status of the project in the State of Jharkhand is at Annexure-A.

(b)	Out of the total length of 256 km, a length of about 41 km is affected due to pending forest clearance. Details of the affected stretches are at Annexure B.

ANNEXURE-A

ANNEXURE REFERRED TO IN REPLY TO PART (a) OF RAJYA SABHA UNSTARRED QUESTION NO. 433 ANSWERED ON 03.12.2025 ASKED BY SMT. MAHUA MAJI REGARDING RANCHI-VARANASI ECONOMIC CORRIDOR

The present status of the Varanasi-Ranchi section in the State of Jharkhand:

| Package | Length (in km) | Total Project Cost (Rs. in crore) | Date of Start | Scheduled/Revised Date of Completion | Status |
| --- | --- | --- | --- | --- | --- |
| Ranchi – Bijupara | 55.00 | 346.33 | Project Completed on 07.08.2019 |  | Work completed. |
| Bijupara – Kuru |  | 229.40 | Project Completed on 25.09.2019 |  |  |
| Kuru – Udaipura | 38.60 | 1274.82 | - | - | 4-laning work awarded & Appointed Date yet to be fixed. |
| Udaipura – Bhogu | 49.94 | 1436.80 | 09.10.2024/ | 31.03.2027 | Physical progress 20%. |
| Bhogu – Sankha | 49.33 | 1517.87 | 09.11.2023 | 30.06.2026 | Physical progress 75%. |
| Sankha – Khajuri | 22.730 | 1129.48 | 07.10.2021 | 15.03.2025 | work completed. |
| Khajuri – Wyndhamganj | 41.060 | 1436.49 | 15.09.2023 | 31.03.2026 | Physical progress 92%. |
| Total | 256.66 | 7,371.19 |  |  |  |

ANNEXURE-B

ANNEXURE REFERRED TO IN REPLY TO PART (b) OF RAJYA SABHA UNSTARRED QUESTION NO. 433 ANSWERED ON 03.12.2025 ASKED BY SMT. MAHUA MAJI REGARDING RANCHI-VARANASI ECONOMIC CORRIDOR

The works affected due to the pending stage-I forest clearance:

| Project / Section | Length (In km) | Status |
| --- | --- | --- |
| Kuru-Udaipura | 38.60 | The work could not be started due to pending Stage-I Forest Clearance. Affected length 15.5 km. |
| Udaipura-Bhogu | 49.94 | The work in 22 km length is yet to be started due to pending Stage-I Forest Clearance. |
| Bhogu- Sankha | 49.33 | The work in 3.5 km length is yet to be started due to pending Stage-I Forest Clearance. |

*****